# Intelligence Domain RAG System

Phased Implementation Roadmap

.NET 10 Technology Stack

Version 1.0

December 2025

# 1. Executive Summary

This document outlines a comprehensive implementation roadmap for a mid-range Intelligence Domain RAG (Retrieval-Augmented Generation) system built on the .NET 10 technology stack. The system is designed as a single-tenant, multi-user platform with team-based access control and agentic reasoning capabilities.

## 1.1 Project Scope

- Single-tenant deployment with multiple users organized into teams

- Team-scoped data source access controlled by administrators

- Hybrid retrieval with vector and keyword search

- Knowledge graph integration for entity relationship analysis

- Agentic reasoning with planning capabilities

- Comprehensive audit logging and compliance features

## 1.2 Implementation Timeline

| Phase | Duration | Focus Area | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1 | Months 1-3 | Foundation | Core infrastructure, auth, basic RAG |
| Phase 2 | Months 4-6 | Data Integration | Multi-source ingestion, NER, KG |
| Phase 3 | Months 7-9 | Agentic System | Planning, tools, multi-agent |
| Phase 4 | Months 10-12 | Production | Security hardening, optimization |

# 2. .NET 10 Technology Stack

The system is built entirely on the .NET 10 ecosystem, leveraging the latest features including Native AOT compilation, improved performance, and enhanced AI/ML integration capabilities.

## 2.1 Core Framework Components

| Component | Technology | Purpose |
| --- | --- | --- |
| Runtime | .NET 10 LTS | Latest LTS with performance improvements |
| Web API | ASP.NET Core 10 | REST API endpoints with OpenAPI |
| Real-time | SignalR | WebSocket for streaming responses |
| Background Jobs | .NET BackgroundService + Hangfire | Ingestion pipelines, scheduled tasks |
| API Gateway | YARP (Yet Another Reverse Proxy) | Routing, rate limiting, load balancing |
| Cloud-Native | .NET Aspire | Service orchestration, observability |

## 2.2 AI/ML Components

| Component | Technology | Purpose |
| --- | --- | --- |
| AI Orchestration | Microsoft Semantic Kernel 2.x | LLM integration, plugins, planning |
| ML Operations | ML.NET 4.x | NER, sentiment analysis, classification |
| ONNX Runtime | Microsoft.ML.OnnxRuntime | Local model inference (embeddings) |
| LLM Inference | LLamaSharp / Ollama API | Local LLM serving (Qwen2.5) |

## 2.3 Data Layer

| Component | Technology | Purpose |
| --- | --- | --- |
| ORM | Entity Framework Core 10 | PostgreSQL data access |
| Vector DB Client | Qdrant.Client | Vector similarity search |
| Graph DB Client | Neo4j.Driver | Knowledge graph queries |
| Caching | StackExchange.Redis | Distributed caching, sessions |
| Search | Elasticsearch.Net / NEST | Full-text search (BM25) |
| Message Queue | MassTransit + RabbitMQ | Async processing, events |

## 2.4 Document Processing

| Component | Technology | Purpose |
| --- | --- | --- |
| PDF Processing | PdfPig / iText7 | PDF text and table extraction |
| Office Documents | DocumentFormat.OpenXml | DOCX, PPTX, XLSX parsing |
| OCR | Tesseract.NET | Image text extraction |
| HTML Parsing | AngleSharp | Web page content extraction |

## 2.5 Security & Identity

| Component | Technology | Purpose |
| --- | --- | --- |
| Authentication | ASP.NET Core Identity | User management, local auth |
| SSO/OIDC | Duende IdentityServer / OpenIddict | Enterprise SSO integration |
| Authorization | Policy-based Authorization | RBAC, team-scoped access |
| Encryption | System.Security.Cryptography | Data encryption at rest |

## 2.6 Frontend & UI

| Component | Technology | Purpose |
| --- | --- | --- |
| Web UI | Blazor WebAssembly / Server | Interactive web application |
| UI Components | MudBlazor / Radzen | Material Design components |
| Graph Visualization | Blazor.Diagrams / Sigma.NET | Knowledge graph display |
| Charts | ApexCharts.Blazor | Analytics dashboards |

## 2.7 Observability

| Component | Technology | Purpose |
| --- | --- | --- |
| Logging | Serilog + Seq | Structured logging |
| Metrics | OpenTelemetry.NET | Metrics collection to Prometheus |
| Tracing | OpenTelemetry.NET | Distributed tracing |
| Health Checks | AspNetCore.HealthChecks | Service health monitoring |
| Dashboards | Grafana | Metrics visualization |

# 3. System Architecture

## 3.1 High-Level Architecture

The system follows a modular, microservices-inspired architecture with clear separation of concerns. All services communicate through well-defined APIs and message queues.

### Service Components

| Service | Project Name | Responsibilities |
| --- | --- | --- |
| API Gateway | IntelRAG.Gateway | Routing, auth validation, rate limiting, request logging |
| Identity Service | IntelRAG.Identity | User/team management, authentication, authorization |
| Query Service | IntelRAG.Query | Query processing, retrieval orchestration, response generation |
| Agent Service | IntelRAG.Agent | Agentic reasoning, planning, tool execution |
| Ingestion Service | IntelRAG.Ingestion | Document processing, embedding generation, indexing |
| Admin Service | IntelRAG.Admin | Data source config, system settings, monitoring |
| Graph Service | IntelRAG.Graph | Knowledge graph operations, entity management |
| Web UI | IntelRAG.Web | Blazor frontend application |

### Solution Structure

IntelRAG.sln

├── src/

│   ├── IntelRAG.Gateway/              # YARP API Gateway

│   ├── IntelRAG.Identity/             # Identity & Auth Service

│   ├── IntelRAG.Query/                # Query Processing Service

│   ├── IntelRAG.Agent/                # Agentic Reasoning Service

│   ├── IntelRAG.Ingestion/            # Document Ingestion Service

│   ├── IntelRAG.Admin/                # Admin & Config Service

│   ├── IntelRAG.Graph/                # Knowledge Graph Service

│   ├── IntelRAG.Web/                  # Blazor Web Application

│   └── IntelRAG.AppHost/              # .NET Aspire Host

├── src/shared/

│   ├── IntelRAG.Domain/               # Domain entities, interfaces

│   ├── IntelRAG.Application/          # Business logic, CQRS handlers

│   ├── IntelRAG.Infrastructure/       # Data access, external services

│   └── IntelRAG.Contracts/            # DTOs, API contracts

├── tests/

│   ├── IntelRAG.UnitTests/

│   ├── IntelRAG.IntegrationTests/

│   └── IntelRAG.E2ETests/

└── docs/

# 4. Phase 1: Foundation (Months 1-3)

Phase 1 establishes the core infrastructure, authentication system, and basic RAG functionality. This phase delivers a working system with essential features.

## 4.1 Phase 1 Objectives

- Set up development environment and CI/CD pipeline

- Implement user authentication and team-based authorization

- Create data source management with team-scoped access

- Build basic document ingestion pipeline

- Implement hybrid retrieval (vector + BM25)

- Develop basic Q&A interface with source citations

- Establish audit logging infrastructure

## 4.2 Sprint Breakdown

### Sprint 1-2: Infrastructure Setup (Weeks 1-4)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Create solution structure with .NET Aspire | IntelRAG.sln scaffold | 3 days |
| Set up PostgreSQL with EF Core migrations | Database schema v1 | 2 days |
| Configure Qdrant vector database | Vector store ready | 2 days |
| Set up Redis for caching | Cache infrastructure | 1 day |
| Configure RabbitMQ with MassTransit | Message bus ready | 2 days |
| Set up Elasticsearch for BM25 search | Search index ready | 2 days |
| Implement Serilog + OpenTelemetry | Logging & tracing | 2 days |
| Create Docker Compose for local dev | docker-compose.yml | 1 day |
| Set up GitHub Actions CI/CD | Build & test pipeline | 2 days |

### Sprint 3-4: Identity & Access Control (Weeks 5-8)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Implement ASP.NET Core Identity | User entity & auth | 3 days |
| Create Team entity and relationships | Team management | 2 days |
| Implement role-based authorization | Admin/Lead/Analyst roles | 2 days |
| Build DataSource entity with team mapping | Data source CRUD | 3 days |
| Create team-scoped authorization policies | Policy handlers | 2 days |
| Implement JWT token generation | Token service | 2 days |
| Build user management API endpoints | User CRUD API | 2 days |
| Build team management API endpoints | Team CRUD API | 2 days |
| Implement audit logging for all actions | AuditLog service | 2 days |

### Sprint 5-6: Basic RAG Pipeline (Weeks 9-12)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Implement document upload endpoint | File upload API | 2 days |
| Build PDF parser with PdfPig | PDF extraction | 3 days |
| Build DOCX parser with OpenXml | Word extraction | 2 days |
| Implement chunking strategies | Semantic chunker | 3 days |
| Integrate BGE-M3 embeddings via ONNX | Embedding service | 3 days |
| Build vector indexing pipeline | Qdrant indexer | 2 days |
| Build BM25 indexing to Elasticsearch | ES indexer | 2 days |
| Implement hybrid retrieval with RRF | Retrieval service | 3 days |
| Integrate LLM via Semantic Kernel | LLM integration | 3 days |
| Build Q&A endpoint with citations | Query API | 3 days |
| Implement response streaming via SignalR | Streaming responses | 2 days |
| Build basic Blazor web interface | Web UI v1 | 5 days |

## 4.3 Phase 1 Database Schema

Core Entities (PostgreSQL)

Users: Id, Email, PasswordHash, FirstName, LastName, Role, TeamId, CreatedAt, LastLoginAt, IsActive

Teams: Id, Name, Description, CreatedBy, CreatedAt

DataSources: Id, Name, Type, ConnectionConfig, RefreshSchedule, Status, CreatedBy, CreatedAt

DataSourceTeamAccess: DataSourceId, TeamId, GrantedBy, GrantedAt

Documents: Id, DataSourceId, FileName, ContentHash, ChunkCount, Status, ProcessedAt

AuditLogs: Id, UserId, Action, ResourceType, ResourceId, Details, IpAddress, Timestamp

## 4.4 Phase 1 Deliverables

- Working authentication system with JWT tokens

- User and team management (Admin functions)

- Data source configuration with team-scoped access

- Document upload and processing (PDF, DOCX)

- Hybrid search (vector + keyword)

- Basic Q&A with source citations

- Audit logging for compliance

- Basic Blazor web interface

# 5. Phase 2: Data Integration & Knowledge Graph (Months 4-6)

Phase 2 expands data source support, implements entity extraction, and builds the knowledge graph for relationship-based queries.

## 5.1 Phase 2 Objectives

- Expand document format support (PPTX, HTML, CSV, Excel)

- Implement Named Entity Recognition (NER)

- Build knowledge graph with Neo4j

- Add database connectors (PostgreSQL, MongoDB)

- Implement RSS/news feed ingestion

- Add reranking for improved precision

- Build investigation workspace feature

## 5.2 Sprint Breakdown

### Sprint 7-8: Extended Document Processing (Weeks 13-16)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Build PPTX parser | PowerPoint extraction | 2 days |
| Build Excel/CSV parser | Spreadsheet extraction | 2 days |
| Implement HTML parser with AngleSharp | Web content extraction | 2 days |
| Add OCR support with Tesseract.NET | Image text extraction | 3 days |
| Build table extraction pipeline | Structured data from tables | 3 days |
| Implement NER with ML.NET | Entity extraction service | 5 days |
| Train custom NER for intel entities | PERSON, ORG, VESSEL, etc. | 5 days |
| Add sentiment analysis | Document sentiment scoring | 2 days |
| Implement language detection | Multi-language support | 2 days |

### Sprint 9-10: Knowledge Graph (Weeks 17-20)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Set up Neo4j with .NET driver | Graph DB ready | 2 days |
| Design intelligence domain schema | Entity/relationship types | 3 days |
| Build entity ingestion pipeline | NER to graph sync | 3 days |
| Implement relationship extraction | Co-occurrence analysis | 4 days |
| Build graph query service | Cypher query builder | 3 days |
| Implement graph expansion in retrieval | Entity-aware retrieval | 3 days |
| Build entity detail API | Entity profile endpoint | 2 days |
| Add graph visualization component | Interactive graph UI | 4 days |

### Sprint 11-12: Data Connectors & Reranking (Weeks 21-24)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Build PostgreSQL connector | SQL data ingestion | 3 days |
| Build MongoDB connector | NoSQL data ingestion | 2 days |
| Implement RSS feed connector | News feed ingestion | 2 days |
| Add scheduled sync with Hangfire | Automated refresh | 2 days |
| Implement cross-encoder reranker | BGE-Reranker integration | 3 days |
| Build investigation workspace backend | Workspace API | 3 days |
| Add query history feature | Query persistence | 2 days |
| Build investigation UI components | Workspace UI | 4 days |
| Implement feedback collection | Thumbs up/down API | 2 days |

## 5.3 Phase 2 Deliverables

- Extended document format support (PPTX, Excel, CSV, HTML)

- OCR for scanned documents

- Named Entity Recognition for intelligence entities

- Knowledge graph with entity relationships

- Graph-enhanced retrieval

- Database connectors (PostgreSQL, MongoDB)

- RSS/news feed integration

- Cross-encoder reranking

- Investigation workspace feature

# 6. Phase 3: Agentic Reasoning System (Months 7-9)

Phase 3 implements the agentic reasoning capabilities with planning, tool execution, and multi-agent orchestration using Microsoft Semantic Kernel.

## 6.1 Phase 3 Objectives

- Implement query analysis and intent classification

- Build task decomposition and planning engine

- Create tool/plugin system with Semantic Kernel

- Implement multi-agent orchestration

- Add working memory and session context

- Build self-evaluation and reflection capabilities

- Implement response quality scoring

## 6.2 Sprint Breakdown

### Sprint 13-14: Semantic Kernel Integration (Weeks 25-28)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Set up Semantic Kernel 2.x | SK integration | 2 days |
| Configure LLM connectors (Ollama/vLLM) | Model connectivity | 2 days |
| Build VectorSearchPlugin | Vector retrieval tool | 2 days |
| Build KeywordSearchPlugin | BM25 retrieval tool | 2 days |
| Build GraphQueryPlugin | Knowledge graph tool | 3 days |
| Build EntityLookupPlugin | Entity detail tool | 2 days |
| Build SanctionsCheckPlugin | Sanctions lookup tool | 2 days |
| Build TimelineBuilderPlugin | Timeline generation tool | 2 days |
| Implement plugin authorization | Tool access control | 2 days |

### Sprint 15-16: Planning & Orchestration (Weeks 29-32)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Build query intent classifier | Intent classification | 3 days |
| Implement query complexity analyzer | Simple/complex routing | 2 days |
| Build Planner Agent with SK Planner | Task decomposition | 4 days |
| Implement DAG-based execution | Parallel task execution | 3 days |
| Build Retriever Agent | Search orchestration | 3 days |
| Build Analyzer Agent | Content analysis | 3 days |
| Build Synthesizer Agent | Response generation | 3 days |
| Implement agent communication | Inter-agent messaging | 2 days |
| Build working memory service | Session context | 2 days |

### Sprint 17-18: Self-Evaluation & Quality (Weeks 33-36)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Build Evaluator Agent | Response evaluation | 3 days |
| Implement completeness scoring | Answer completeness check | 2 days |
| Implement faithfulness scoring | Hallucination detection | 3 days |
| Build iterative refinement loop | Self-correction | 3 days |
| Implement confidence scoring | Response confidence | 2 days |
| Add reasoning trace logging | Explainable AI | 2 days |
| Build multi-turn conversation handler | Context preservation | 3 days |
| Implement suggested follow-ups | Related questions | 2 days |
| Update UI for agentic features | Reasoning trace UI | 4 days |

## 6.3 Semantic Kernel Plugin Architecture

Plugin Registration Example:

public class IntelligencePlugins {

[KernelFunction, Description("Search vector store for relevant documents")]

public async Task<string> VectorSearchAsync(

[Description("Search query")] string query,

[Description("Number of results")] int topK = 10) { ... }

[KernelFunction, Description("Query knowledge graph for entity relationships")]

public async Task<string> GraphQueryAsync(

[Description("Entity name")] string entity,

[Description("Max hops")] int maxHops = 2) { ... }

}

## 6.4 Phase 3 Deliverables

- Semantic Kernel integration with custom plugins

- Query intent classification and routing

- Task decomposition and planning

- Multi-agent orchestration (Planner, Retriever, Analyzer, Synthesizer)

- Self-evaluation with faithfulness and completeness scoring

- Working memory for conversation context

- Reasoning trace visualization

- Multi-turn conversation support

# 7. Phase 4: Production Readiness (Months 10-12)

Phase 4 focuses on security hardening, performance optimization, comprehensive testing, and production deployment preparation.

## 7.1 Phase 4 Objectives

- Implement security hardening and penetration testing

- Add semantic caching for performance

- Build comprehensive admin dashboard

- Implement report generation and export

- Complete end-to-end testing

- Performance tuning and optimization

- Documentation and training materials

## 7.2 Sprint Breakdown

### Sprint 19-20: Security & Caching (Weeks 37-40)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Implement input validation/sanitization | Prompt injection prevention | 3 days |
| Add output content filtering | Sensitive data blocking | 2 days |
| Implement rate limiting per user/team | Abuse prevention | 2 days |
| Add API key management | External API auth | 2 days |
| Implement semantic cache with Redis | Similar query caching | 3 days |
| Add embedding cache | Computed embedding storage | 2 days |
| Implement LLM response cache | Response caching | 2 days |
| Security audit and penetration testing | Security report | 5 days |
| Implement SSO integration (OIDC) | Enterprise auth | 3 days |

### Sprint 21-22: Admin & Reporting (Weeks 41-44)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Build admin dashboard UI | System overview page | 4 days |
| Add user/team management UI | User admin pages | 3 days |
| Build data source management UI | Data source admin | 3 days |
| Implement ingestion monitoring | Pipeline status dashboard | 2 days |
| Add audit log viewer | Log search/export UI | 3 days |
| Build usage analytics dashboard | Query statistics | 3 days |
| Implement PDF report generation | Investigation reports | 3 days |
| Add Word document export | DOCX reports | 2 days |
| Implement data export (JSON, CSV) | Structured export | 2 days |

### Sprint 23-24: Testing & Deployment (Weeks 45-48)

| Task | Deliverable | Effort |
| --- | --- | --- |
| Write comprehensive unit tests | >80% code coverage | 5 days |
| Build integration test suite | API integration tests | 4 days |
| Implement E2E tests with Playwright | UI automation tests | 4 days |
| RAG evaluation pipeline (RAGAS) | Quality metrics | 3 days |
| Performance load testing | Benchmark results | 3 days |
| Query optimization and tuning | Performance improvements | 3 days |
| Create Kubernetes deployment manifests | K8s configs | 3 days |
| Build Helm charts | Deployment automation | 2 days |
| Write technical documentation | API docs, architecture | 4 days |
| Create user guide and training | User documentation | 3 days |

## 7.3 Phase 4 Deliverables

- Security hardened application

- SSO/OIDC integration

- Semantic caching for improved latency

- Comprehensive admin dashboard

- Report generation (PDF, DOCX, JSON, CSV)

- Complete test suite (unit, integration, E2E)

- RAG evaluation pipeline

- Kubernetes deployment configurations

- Technical and user documentation

# 8. NuGet Package Dependencies

## 8.1 Core Dependencies

| Package | Version | Purpose |
| --- | --- | --- |
| Microsoft.AspNetCore.App | 10.0.0 | ASP.NET Core framework |
| Microsoft.EntityFrameworkCore.Npgsql | 10.0.0 | PostgreSQL EF Core |
| Microsoft.SemanticKernel | 2.0.0 | AI orchestration |
| Microsoft.ML | 4.0.0 | ML.NET runtime |
| Microsoft.ML.OnnxRuntime | 1.19.0 | ONNX inference |
| Qdrant.Client | 1.12.0 | Vector database |
| Neo4j.Driver | 5.25.0 | Graph database |
| StackExchange.Redis | 2.8.0 | Redis client |
| NEST | 7.17.0 | Elasticsearch client |
| MassTransit.RabbitMQ | 8.3.0 | Message bus |
| Hangfire.AspNetCore | 1.8.0 | Background jobs |

## 8.2 Document Processing

| Package | Version | Purpose |
| --- | --- | --- |
| PdfPig | 0.1.9 | PDF parsing |
| DocumentFormat.OpenXml | 3.2.0 | Office documents |
| AngleSharp | 1.1.0 | HTML parsing |
| Tesseract | 5.2.0 | OCR |
| CsvHelper | 33.0.0 | CSV processing |
| ExcelDataReader | 3.7.0 | Excel reading |

## 8.3 Security & Identity

| Package | Version | Purpose |
| --- | --- | --- |
| Microsoft.AspNetCore.Identity.EntityFrameworkCore | 10.0.0 | User management |
| Microsoft.AspNetCore.Authentication.JwtBearer | 10.0.0 | JWT auth |
| OpenIddict.AspNetCore | 5.8.0 | OIDC server |
| BCrypt.Net-Next | 4.0.3 | Password hashing |

## 8.4 Observability

| Package | Version | Purpose |
| --- | --- | --- |
| Serilog.AspNetCore | 8.0.0 | Structured logging |
| Serilog.Sinks.Seq | 8.0.0 | Log aggregation |
| OpenTelemetry.Extensions.Hosting | 1.10.0 | Telemetry |
| OpenTelemetry.Exporter.Prometheus.AspNetCore | 1.10.0 | Metrics export |
| AspNetCore.HealthChecks.UI | 8.0.0 | Health monitoring |

## 8.5 Frontend (Blazor)

| Package | Version | Purpose |
| --- | --- | --- |
| MudBlazor | 7.12.0 | UI components |
| Blazor.Diagrams | 3.0.0 | Graph visualization |
| ApexCharts.Blazor | 3.4.0 | Charts |
| Blazored.LocalStorage | 4.5.0 | Browser storage |

# 9. Hardware Requirements

## 9.1 Development Environment

| Component | Minimum | Recommended |
| --- | --- | --- |
| CPU | 8 cores | 16 cores |
| RAM | 32GB | 64GB |
| GPU | RTX 3080 (10GB) | RTX 4090 (24GB) |
| Storage | 500GB NVMe | 1TB NVMe |

## 9.2 Production Environment

| Component | Minimum | Recommended |
| --- | --- | --- |
| CPU | 32 cores | 64 cores |
| RAM | 128GB | 256GB |
| GPU | 1x NVIDIA A100 40GB | 2x NVIDIA A100 80GB |
| Storage | 2TB NVMe | 4TB NVMe RAID |
| Network | 10 Gbps | 25 Gbps |

# 10. Implementation Timeline Summary

## 10.1 Gantt Overview

| Phase | M1 | M2 | M3 | M4 | M5 | M6 |
| --- | --- | --- | --- | --- | --- | --- |
| P1: Foundation | ████ | ████ | ████ |  |  |  |
| P2: Data/KG |  |  |  | ████ | ████ | ████ |

| Phase | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- |
| P3: Agentic | ████ | ████ | ████ |  |  |  |
| P4: Production |  |  |  | ████ | ████ | ████ |

## 10.2 Key Milestones

| Milestone | Target Date | Success Criteria |
| --- | --- | --- |
| M1: Infrastructure | End of Month 1 | All databases operational, CI/CD working |
| M2: Auth Complete | End of Month 2 | User/team management functional |
| M3: Basic RAG | End of Month 3 | Document Q&A with citations working |
| M4: Extended Formats | End of Month 4 | All document formats supported |
| M5: Knowledge Graph | End of Month 5 | Entity graph queryable |
| M6: GraphRAG | End of Month 6 | Graph-enhanced retrieval working |
| M7: Plugins | End of Month 7 | All SK plugins operational |
| M8: Agents | End of Month 8 | Multi-agent orchestration working |
| M9: Self-Eval | End of Month 9 | Quality scoring implemented |
| M10: Security | End of Month 10 | Security audit passed |
| M11: Admin UI | End of Month 11 | Admin dashboard complete |
| M12: Production | End of Month 12 | System deployed, documentation complete |

# 11. Risk Management

## 11.1 Technical Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| LLM inference latency too high | Medium | High | Use vLLM with batching, implement caching, model quantization |
| Vector search scaling issues | Low | Medium | Qdrant clustering, index optimization, sharding |
| NER accuracy insufficient | Medium | Medium | Custom model training, ensemble methods, human review |
| Graph query performance | Medium | Medium | Neo4j indexing, query optimization, caching |
| Semantic Kernel limitations | Low | High | Fallback to custom orchestration, engage Microsoft support |

## 11.2 Project Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Scope creep | High | Medium | Strict change control, prioritized backlog, MVP focus |
| Resource availability | Medium | High | Cross-training, documentation, modular design |
| Integration complexity | Medium | Medium | Early integration testing, clear API contracts |
| Requirements changes | Medium | Medium | Agile methodology, regular stakeholder reviews |

# 12. Recommended Team Structure

## 12.1 Core Team

| Role | Count | Responsibilities |
| --- | --- | --- |
| Tech Lead / Architect | 1 | Architecture decisions, code reviews, technical direction |
| Senior Backend Developer | 2 | API development, database design, integrations |
| ML/AI Engineer | 1 | LLM integration, embeddings, NER, model optimization |
| Frontend Developer | 1 | Blazor UI development, UX implementation |
| DevOps Engineer | 1 | CI/CD, infrastructure, monitoring, deployment |
| QA Engineer | 1 | Test automation, quality assurance, UAT |

## 12.2 Extended Team (As Needed)

| Role | Phase | Responsibilities |
| --- | --- | --- |
| Security Specialist | Phase 4 | Security audit, penetration testing, compliance |
| UX Designer | Phase 1, 4 | UI/UX design, user research, wireframes |
| Technical Writer | Phase 4 | Documentation, user guides, API docs |
| Domain Expert (Intel) | All Phases | Requirements validation, domain knowledge, UAT |

# 13. Success Criteria

## 13.1 Performance Metrics

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Query Response Time (P50) | < 3 seconds | OpenTelemetry latency tracking |
| Query Response Time (P95) | < 10 seconds | OpenTelemetry latency tracking |
| Retrieval Recall@10 | > 0.85 | RAGAS evaluation pipeline |
| Answer Faithfulness | > 0.85 | RAGAS faithfulness metric |
| Answer Relevancy | > 0.80 | RAGAS relevancy metric |
| System Uptime | > 99.5% | Health check monitoring |
| Concurrent Users | > 50 | Load testing with k6 |

## 13.2 Quality Gates

- Code coverage > 80% for unit tests

- Zero critical/high severity vulnerabilities

- All API endpoints documented with OpenAPI

- Security audit passed

- User acceptance testing signed off

- Performance benchmarks met

# 14. Appendix: Quick Reference

## 14.1 CLI Commands

# Create solution

dotnet new sln -n IntelRAG

# Add .NET Aspire AppHost

dotnet new aspire-apphost -n IntelRAG.AppHost

# Add Web API project

dotnet new webapi -n IntelRAG.Query -o src/IntelRAG.Query

# Add Blazor project

dotnet new blazorwasm -n IntelRAG.Web -o src/IntelRAG.Web

# Add class library

dotnet new classlib -n IntelRAG.Domain -o src/shared/IntelRAG.Domain

# Run with Aspire

dotnet run --project src/IntelRAG.AppHost

## 14.2 Docker Services

# docker-compose.yml services

- postgres:16          # PostgreSQL database

- qdrant/qdrant:v1.12  # Vector database

- neo4j:5.25           # Graph database

- redis:7              # Cache

- elasticsearch:8.15   # Full-text search

- rabbitmq:3-management # Message queue

- ollama/ollama        # LLM inference

- datalust/seq         # Log aggregation

- grafana/grafana      # Dashboards

- prom/prometheus      # Metrics

— End of Document —